## Supplier Master List
🏭 Pinnacle Construction & Development Corporation — SUPPLIER MASTER LIST
Accredited Vendors & Contractors · Procurement Division · As of 2024–2026
Supplier ID | Company Name | Category | Head Office Address | Contact Person | Phone | Email Address | TIN | Payment Terms | Credit Limit (₱K) | Performance Rating | Status | Lead Days | Currency
SUP-001 | Holcim Philippines Inc. | Cement & Concrete | 3rd Fl., 8 Rockwell, Makati City | Engr. Ramon Dela Cruz | (02) 8898-1000 | sales.ph@holcim.com | 000-123-456-000 | 30 Days Net | 5000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-002 | Republic Cement & Building Materials Inc. | Cement & Concrete | 28F Burgundy Corporate Tower, Ortigas, Pasig | Ms. Carla Reyes | (02) 8634-2000 | procurement@republiccement.com | 000-234-567-000 | 45 Days Net | 3000 | ⭐⭐⭐⭐ Good | ✅ Active | 10 | PHP
SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | 7F 1880 Eastwood Ave., Libis, QC | Mr. Jose Santos | (02) 8884-1000 | info.ph@cemex.com | 000-345-678-000 | 30 Days Net | 4000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | 54 Eulogio Rodriguez Jr. Ave., Quezon City | Engr. Patrick Lim | (02) 8911-0000 | sales@steelasia.com | 000-456-789-000 | 30 Days Net | 8000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 14 | PHP
SUP-005 | Capital Steel Corporation | Steel & Metal | Pinagbuhatan, Pasig City | Mr. Benjamin Tan | (02) 8641-5555 | info@capitalsteel.com.ph | 000-567-890-000 | 45 Days Net | 5000 | ⭐⭐⭐⭐ Good | ✅ Active | 14 | PHP
SUP-006 | Peerless Metal Industries Inc. | Steel & Metal | 101 A. Bonifacio Ave., Mandaluyong | Ms. Rowena Garcia | (02) 8532-1234 | sales@peerlessmetal.ph | 000-678-901-000 | 30 Days Net | 2000 | ⭐⭐⭐ Fair | ✅ Active | 10 | PHP
SUP-007 | Wilcon Depot Inc. | Hardware & Tools | No. 60 E. Rodriguez Sr. Ave., QC | Mr. Eduardo Cruz | (02) 8911-5555 | corporate@wilcon.com.ph | 000-789-012-000 | 30 Days Net | 1500 | ⭐⭐⭐⭐ Good | ✅ Active | 3 | PHP
SUP-008 | Ace Hardware Philippines Inc. | Hardware & Tools | Robinsons Galleria, Ortigas, Pasig | Ms. Maria Fernandez | (02) 8631-4567 | corporate@acehardware.ph | 000-890-123-000 | 30 Days Net | 1000 | ⭐⭐⭐⭐ Good | ✅ Active | 3 | PHP
SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | 5F 6750 Ayala Ave., Makati | Engr. Allan Mendoza | (02) 8888-5900 | info.ph@se.com | 000-901-234-000 | 45 Days Net | 3000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 14 | PHP
SUP-010 | Siemens Philippines Inc. | Electrical & Mechanical | 30F GT Tower, Ayala Ave., Makati | Engr. Cristina Villanueva | (02) 8819-7000 | info@siemens.com.ph | 001-012-345-000 | 45 Days Net | 4000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 21 | PHP
SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | 14F Zuellig Bldg, Makati Ave., Makati | Mr. Marco Torres | (02) 8555-1234 | abb.ph@ph.abb.com | 001-123-456-000 | 30 Days Net | 3500 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 14 | PHP
SUP-012 | Legrand Philippines Inc. | Electrical & Mechanical | Unit 2, 1322 Apolinario St., Makati | Ms. Joyce Castillo | (02) 8899-7777 | info@legrand.ph | 001-234-567-000 | 30 Days Net | 1500 | ⭐⭐⭐⭐ Good | ✅ Active | 10 | PHP
SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Center, Bonifacio Global City, Taguig | Ms. Angela Ramos | (02) 8818-3000 | ph.info@mmm.com | 001-345-678-000 | 30 Days Net | 1000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-014 | Honeywell Philippines Inc. | Safety Equipment | 18F Ayala Triangle, Paseo de Roxas, Makati | Mr. Victor Bautista | (02) 8867-4444 | info.ph@honeywell.com | 001-456-789-000 | 45 Days Net | 2000 | ⭐⭐⭐⭐ Good | ✅ Active | 14 | PHP
SUP-015 | Petron Corporation | Fuel & Lubricants | Petron Megaplaza, Makati City | Mr. Rodrigo Soriano | (02) 8884-5555 | corporate@petron.com | 001-567-890-000 | 15 Days Net | 2000 | ⭐⭐⭐⭐ Good | ✅ Active | 3 | PHP
SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | 156 Valero St., Salcedo Vill., Makati | Ms. Grace Aquino | (02) 8884-8888 | shellph@shell.com | 001-678-901-000 | 15 Days Net | 2000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 3 | PHP
SUP-017 | Chevron Philippines Inc. | Fuel & Lubricants | 6750 Ayala Ave., Makati City | Mr. Dennis Pascual | (02) 8815-5000 | info.ph@chevron.com | 001-789-012-000 | 15 Days Net | 1500 | ⭐⭐⭐⭐ Good | ✅ Active | 3 | PHP
SUP-018 | HP Philippines Inc. | IT Equipment | 31F Rufino Pacific Tower, Makati | Ms. Karen Dela Torre | (02) 8888-9090 | hp.ph@hp.com | 001-890-123-000 | 30 Days Net | 2000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-019 | Dell Technologies Philippines | IT Equipment | 8F Ayala Northexchange, Quezon Ave., QC | Mr. Alvin Lorenzo | (02) 8861-0700 | dell.ph@dell.com | 001-901-234-000 | 30 Days Net | 3000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-020 | Lenovo Philippines | IT Equipment | 23F 8 Rockwell, Makati City | Ms. Shirley Mendoza | (02) 8403-7000 | lenovo.ph@lenovo.com | 002-012-345-000 | 30 Days Net | 2500 | ⭐⭐⭐⭐ Good | ✅ Active | 10 | PHP
SUP-021 | Canon Marketing Philippines Inc. | IT Equipment | 20F Robinsons Equitable Tower, Ortigas | Engr. Jason Navarro | (02) 8633-9999 | canon.ph@canon.com.ph | 002-123-456-000 | 30 Days Net | 1500 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 7 | PHP
SUP-022 | Epson Philippines Corporation | IT Equipment | 8F Robinsons Cybergate, Mandaluyong | Ms. Michelle Uy | (02) 8706-2659 | epson.ph@epson.com.ph | 002-234-567-000 | 30 Days Net | 1500 | ⭐⭐⭐⭐ Good | ✅ Active | 7 | PHP
SUP-023 | National Book Store Inc. | Office Supplies | Quad Alpha Centrum, Shaw Blvd., Mandaluyong | Ms. Rowena Villanueva | (02) 8631-7700 | corporate@nbs.ph | 002-345-678-000 | 30 Days Net | 500 | ⭐⭐⭐⭐ Good | ✅ Active | 3 | PHP
SUP-024 | Goldilocks Bookware & Office Supply | Office Supplies | 1168 Paz Guanzon St., Paco, Manila | Mr. Frederick Santos | (02) 8563-2222 | office@goldilocks.com.ph | 002-456-789-000 | 30 Days Net | 300 | ⭐⭐⭐ Fair | ✅ Active | 3 | PHP
SUP-025 | PLDT Inc. | Telecommunications | Ramon Cojuangco Bldg., Makati Ave., Makati | Ms. Elaine Reyes | (02) 8816-5300 | enterprise@pldt.com | 002-567-890-000 | 30 Days Net | 500 | ⭐⭐⭐⭐ Good | ✅ Active | 30 | PHP
SUP-026 | Globe Telecom Inc. | Telecommunications | The Globe Tower, BGC, Taguig | Mr. Ronald Cruz | (02) 8730-1288 | business@globe.com.ph | 002-678-901-000 | 30 Days Net | 500 | ⭐⭐⭐⭐ Good | ✅ Active | 30 | PHP
SUP-027 | Meralco (Manila Electric Company) | Utilities | Lopez Bldg., Meralco Ave., Ortigas, Pasig | Ms. Analiza Fernandez | (02) 8672-5311 | corporate@meralco.com.ph | 002-789-012-000 | 30 Days Net | 1000 | ⭐⭐⭐⭐ Good | ✅ Active | 30 | PHP
SUP-028 | Maynilad Water Services Inc. | Utilities | MWSS Compound, Balara, QC | Mr. Gilbert Torres | (02) 8981-6400 | maynilad@maynilad.com.ph | 002-890-123-000 | 30 Days Net | 500 | ⭐⭐⭐ Fair | ✅ Active | 30 | PHP
SUP-029 | Lafarge Republic Inc. | Cement & Concrete | 23F GT Tower, Ayala Ave., Makati | Engr. Benedicto Ramos | (02) 8811-1000 | lafarge.ph@lafarge.com | 002-901-234-000 | 30 Days Net | 3000 | ⭐⭐⭐⭐ Good | ✅ Active | 10 | PHP
SUP-030 | Pacific Paint (Boysen) Philippines Inc. | Construction Materials | 66 Industrial Road, Mandaluyong | Ms. Sandra Castillo | (02) 8531-3456 | boysen@boysen.com.ph | 003-012-345-000 | 30 Days Net | 800 | ⭐⭐⭐⭐ Good | ✅ Active | 5 | PHP
SUP-031 | Davies Paints Philippines Inc. | Construction Materials | 76 San Rafael St., Mandaluyong | Mr. Arnold Bautista | (02) 8532-8888 | davies@davies.com.ph | 003-123-456-000 | 30 Days Net | 600 | ⭐⭐⭐⭐ Good | ✅ Active | 5 | PHP
SUP-032 | Neltex Development Co. Inc. | Construction Materials | Km 19 West Service Rd., Paranaque | Engr. Evelyn Dela Cruz | (02) 8829-7890 | neltex@neltex.com.ph | 003-234-567-000 | 30 Days Net | 1000 | ⭐⭐⭐⭐ Good | ✅ Active | 7 | PHP
SUP-033 | Vyniles Corporation Philippines | Construction Materials | Km 14, East Service Rd., Paranaque | Mr. Samuel Garcia | (02) 8829-5678 | vyniles@vyniles.ph | 003-345-678-000 | 45 Days Net | 1200 | ⭐⭐⭐ Fair | ⚠ Probation | 10 | PHP
SUP-034 | Dowell Schlumberger Philippines | Engineering Services | 19F Petron Megaplaza, Makati | Engr. Maricel Santos | (02) 8819-8000 | ph@slb.com | 003-456-789-000 | 45 Days Net | 5000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 21 | PHP
SUP-035 | EEI Corporation | Engineering Services | EEI Bldg, Rodriguez Ave., Quezon City | Mr. Roderick Mendoza | (02) 8912-2100 | info@eei.com.ph | 003-567-890-000 | 30 Days Net | 10000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 30 | PHP
SUP-036 | Sta. Clara International Corporation | Engineering Services | SCIC Bldg, Ayala Ave., Makati | Ms. Patricia Villanueva | (02) 8812-1111 | info@staclaraintl.com | 003-678-901-000 | 30 Days Net | 8000 | ⭐⭐⭐⭐ Good | ✅ Active | 30 | PHP
SUP-037 | Komatsu Philippines Inc. | Heavy Equipment | Komatsu Bldg, South Superhighway, Las Piñas | Engr. Reynaldo Torres | (02) 8807-5000 | info.ph@komatsu.com | 003-789-012-000 | 45 Days Net | 20000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 30 | USD
SUP-038 | Volvo Financial Services Philippines | Heavy Equipment | 20F RCBC Plaza, Makati City | Mr. Henry Pascual | (02) 8884-2222 | vfsphilippines@volvo.com | 003-890-123-000 | 60 Days Net | 15000 | ⭐⭐⭐⭐⭐ Excellent | ✅ Active | 45 | USD
SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | One Corporate Centre, Julia Vargas, Ortigas | Ms. Divina Aquino | (02) 8706-9000 | aggregates.ph@holcimtrd.com | 003-901-234-000 | 30 Days Net | 2000 | ⭐⭐⭐⭐ Good | ✅ Active | 5 | PHP
SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Calamba, Laguna | Mr. Augusto Lorenzo | (049) 545-1234 | pic@phindcorp.com | 004-012-345-000 | 30 Days Net | 800 | ⭐⭐⭐ Fair | ✅ Active | 14 | PHP

## PO Register
📋 Pinnacle Construction & Development Corporation — PURCHASE ORDER REGISTER 2024–2026
All Purchase Orders · Procurement Division · Reference: PCDC-PROC-2024 to 2026
PO Number | Supplier ID | Supplier Name | Category | Description | PO Date | Required Delivery | Qty | Unit Cost (₱) | Discount % | Disc. Amount (₱) | Subtotal (₱) | VAT 12% (₱) | Total PO Value (₱) | Payment Terms | Approved By | PO Status | Remarks
PO-2024-001 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Portland Cement Type I (40kg bag) | 2024-01-08 | 2024-01-15 | 2000 | 285 | 200% | 11400 | 558600 | 67032 | 625632 | 30 Days Net | VP-Operations | ✅ Closed | Site A - Foundation works
PO-2024-002 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 10mm x 6m | 2024-01-10 | 2024-01-24 | 5000 | 195 | 150% | 14625 | 960375 | 115245 | 1075620 | 30 Days Net | VP-Operations | ✅ Closed | Site A - Rebar works
PO-2024-003 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 12mm x 6m | 2024-01-10 | 2024-01-24 | 3000 | 280 | 150% | 12600 | 827400 | 99288 | 926688 | 30 Days Net | VP-Operations | ✅ Closed | Site A - Rebar works
PO-2024-004 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Plywood Marine 1/2 inch (4x8ft) | 2024-01-15 | 2024-01-18 | 500 | 1250 | 0% | 0 | 625000 | 75000 | 700000 | 30 Days Net | Procurement Mgr | ✅ Closed | Formworks
PO-2024-005 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Circuit Breaker 100A 3-Phase MCCB | 2024-01-18 | 2024-02-01 | 50 | 8500 | 500% | 21250 | 403750 | 48450 | 452200 | 45 Days Net | VP-Operations | ✅ Closed | Electrical panel Site A
PO-2024-006 | SUP-013 | 3M Philippines Inc. | Safety Equipment | Safety Helmet (ANSI Z89.1) | 2024-01-20 | 2024-01-27 | 200 | 350 | 0% | 0 | 70000 | 8400 | 78400 | 30 Days Net | Safety Officer | ✅ Closed | New hires PPE
PO-2024-007 | SUP-013 | 3M Philippines Inc. | Safety Equipment | Safety Vest High-Visibility XL | 2024-01-20 | 2024-01-27 | 300 | 220 | 0% | 0 | 66000 | 7920 | 73920 | 30 Days Net | Safety Officer | ✅ Closed | New hires PPE
PO-2024-008 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial Grade, liters) | 2024-01-25 | 2024-01-28 | 10000 | 69.5 | 0% | 0 | 695000 | 83400 | 778400 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Jan
PO-2024-009 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Portland Cement Type I (40kg bag) | 2024-02-05 | 2024-02-12 | 3000 | 285 | 200% | 17100 | 837900 | 100548 | 938448 | 30 Days Net | VP-Operations | ✅ Closed | Site A - Slab 2F
PO-2024-010 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Washed Sand (cubic meter) | 2024-02-07 | 2024-02-14 | 200 | 1800 | 0% | 0 | 360000 | 43200 | 403200 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A
PO-2024-011 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Crushed Gravel 3/4 inch (cubic meter) | 2024-02-07 | 2024-02-14 | 150 | 2200 | 0% | 0 | 330000 | 39600 | 369600 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A
PO-2024-012 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 16mm x 6m | 2024-02-12 | 2024-02-26 | 2000 | 480 | 150% | 14400 | 945600 | 113472 | 1059072 | 30 Days Net | VP-Operations | ✅ Closed | Site A - Columns
PO-2024-013 | SUP-018 | HP Philippines Inc. | IT Equipment | HP LaserJet Pro M404dn Printer | 2024-02-15 | 2024-02-22 | 10 | 18500 | 500% | 9250 | 175750 | 21090 | 196840 | 30 Days Net | IT Manager | ✅ Closed | Office upgrade
PO-2024-014 | SUP-023 | National Book Store Inc. | Office Supplies | Bond Paper A4 80gsm (ream) | 2024-02-18 | 2024-02-21 | 200 | 265 | 0% | 0 | 53000 | 6360 | 59360 | 30 Days Net | Admin Officer | ✅ Closed | Q1 office supply
PO-2024-015 | SUP-023 | National Book Store Inc. | Office Supplies | Ballpen Pilot G-2 (box of 12) | 2024-02-18 | 2024-02-21 | 50 | 280 | 0% | 0 | 14000 | 1680 | 15680 | 30 Days Net | Admin Officer | ✅ Closed | Q1 office supply
PO-2024-016 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Unleaded Gasoline (liters) | 2024-02-20 | 2024-02-23 | 3000 | 72.8 | 0% | 0 | 218400 | 26208 | 244608 | 15 Days Net | Admin Manager | ✅ Closed | Company vehicles Feb
PO-2024-017 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Load Break Switch 100A 3-Phase | 2024-03-01 | 2024-03-15 | 20 | 22000 | 500% | 22000 | 418000 | 50160 | 468160 | 45 Days Net | VP-Operations | ✅ Closed | Main electrical Site A
PO-2024-018 | SUP-010 | Siemens Philippines Inc. | Electrical & Mechanical | Siemens SENTRON PAC3200 Power Meter | 2024-03-04 | 2024-03-25 | 5 | 85000 | 300% | 12750 | 412250 | 49470 | 461720 | 45 Days Net | VP-Operations | ✅ Closed | Energy monitoring
PO-2024-019 | SUP-030 | Pacific Paint (Boysen) Philippines Inc. | Construction Materials | Boysen Permacoat Flat White (4L) | 2024-03-07 | 2024-03-12 | 300 | 580 | 0% | 0 | 174000 | 20880 | 194880 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A - Painting
PO-2024-020 | SUP-032 | Neltex Development Co. Inc. | Construction Materials | PVC Pipe 4 inch x 6m (S-1000) | 2024-03-10 | 2024-03-17 | 500 | 425 | 0% | 0 | 212500 | 25500 | 238000 | 30 Days Net | Procurement Mgr | ✅ Closed | Plumbing rough-in
PO-2024-021 | SUP-032 | Neltex Development Co. Inc. | Construction Materials | PVC Elbow 4 inch 90-degree | 2024-03-10 | 2024-03-17 | 300 | 85 | 0% | 0 | 25500 | 3060 | 28560 | 30 Days Net | Procurement Mgr | ✅ Closed | Plumbing rough-in
PO-2024-022 | SUP-037 | Komatsu Philippines Inc. | Heavy Equipment | Komatsu PC200-10 Excavator (unit) | 2024-03-15 | 2024-04-15 | 1 | 8500000 | 0% | 0 | 8500000 | 1020000 | 9520000 | 45 Days Net | CEO | ✅ Closed | Site B capital equipment
PO-2024-023 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial Grade, liters) | 2024-03-25 | 2024-03-28 | 12000 | 70.2 | 0% | 0 | 842400 | 101088 | 943488 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Mar
PO-2024-024 | SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | CEMEX Asenso Ready Mix Cement (40kg) | 2024-04-02 | 2024-04-09 | 2500 | 290 | 200% | 14500 | 710500 | 85260 | 795760 | 30 Days Net | VP-Operations | ✅ Closed | Site B - Foundation
PO-2024-025 | SUP-005 | Capital Steel Corporation | Steel & Metal | Steel C-Purlins 2x4 (6m) | 2024-04-05 | 2024-04-19 | 1000 | 380 | 100% | 3800 | 376200 | 45144 | 421344 | 45 Days Net | VP-Operations | ✅ Closed | Roofing structure
PO-2024-026 | SUP-006 | Peerless Metal Industries Inc. | Steel & Metal | Galvanized Iron Roof Sheet G26 (4m) | 2024-04-08 | 2024-04-18 | 800 | 520 | 0% | 0 | 416000 | 49920 | 465920 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A roofing
PO-2024-027 | SUP-012 | Legrand Philippines Inc. | Electrical & Mechanical | Legrand Mosaic Switch 2-gang | 2024-04-10 | 2024-04-20 | 500 | 280 | 500% | 7000 | 133000 | 15960 | 148960 | 30 Days Net | VP-Operations | ✅ Closed | Interior electrical
PO-2024-028 | SUP-012 | Legrand Philippines Inc. | Electrical & Mechanical | Legrand Socket Outlet 3-pin | 2024-04-10 | 2024-04-20 | 800 | 320 | 500% | 12800 | 243200 | 29184 | 272384 | 30 Days Net | VP-Operations | ✅ Closed | Interior electrical
PO-2024-029 | SUP-014 | Honeywell Philippines Inc. | Safety Equipment | Honeywell BW Clip4 Gas Detector | 2024-04-15 | 2024-04-22 | 20 | 18500 | 0% | 0 | 370000 | 44400 | 414400 | 45 Days Net | Safety Officer | ✅ Closed | Confined space works
PO-2024-030 | SUP-023 | National Book Store Inc. | Office Supplies | Arch Lever File (box of 10) | 2024-04-18 | 2024-04-21 | 30 | 890 | 0% | 0 | 26700 | 3204 | 29904 | 30 Days Net | Admin Officer | ✅ Closed | Q2 office supply
PO-2024-031 | SUP-019 | Dell Technologies Philippines | IT Equipment | Dell OptiPlex 7010 Desktop PC | 2024-05-02 | 2024-05-09 | 15 | 42000 | 500% | 31500 | 598500 | 71820 | 670320 | 30 Days Net | IT Manager | ✅ Closed | Finance dept upgrade
PO-2024-032 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Wallright Masonry Cement 40kg | 2024-05-06 | 2024-05-13 | 1500 | 310 | 200% | 9300 | 455700 | 54684 | 510384 | 30 Days Net | VP-Operations | ✅ Closed | Site B - Block laying
PO-2024-033 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Washed Sand (cubic meter) | 2024-05-08 | 2024-05-15 | 300 | 1800 | 0% | 0 | 540000 | 64800 | 604800 | 30 Days Net | Procurement Mgr | ✅ Closed | Site B
PO-2024-034 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 20mm x 6m (High Tensile) | 2024-05-10 | 2024-05-24 | 1500 | 680 | 200% | 20400 | 999600 | 119952 | 1119552 | 30 Days Net | VP-Operations | ✅ Closed | Site B - Girder
PO-2024-035 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider iC60N 63A MCB 3P | 2024-05-15 | 2024-05-29 | 100 | 1850 | 500% | 9250 | 175750 | 21090 | 196840 | 45 Days Net | VP-Operations | ✅ Closed | Distribution boards
PO-2024-036 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel Shell V-Power Nitro+ | 2024-05-20 | 2024-05-23 | 2000 | 74.5 | 0% | 0 | 149000 | 17880 | 166880 | 15 Days Net | Admin Manager | ✅ Closed | Executive vehicles
PO-2024-037 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Peltor Ear Muff H10A | 2024-05-22 | 2024-05-29 | 150 | 1850 | 0% | 0 | 277500 | 33300 | 310800 | 30 Days Net | Safety Officer | ✅ Closed | Noise PPE
PO-2024-038 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M 6200 Half-Face Respirator | 2024-05-22 | 2024-05-29 | 100 | 2200 | 0% | 0 | 220000 | 26400 | 246400 | 30 Days Net | Safety Officer | ✅ Closed | Dust PPE
PO-2024-039 | SUP-020 | Lenovo Philippines | IT Equipment | Lenovo ThinkPad E15 Gen5 Laptop | 2024-06-03 | 2024-06-10 | 8 | 68000 | 500% | 27200 | 516800 | 62016 | 578816 | 30 Days Net | IT Manager | ✅ Closed | Engineers' laptops
PO-2024-040 | SUP-021 | Canon Marketing Philippines Inc. | IT Equipment | Canon imageCLASS MF752Cdw MFP | 2024-06-05 | 2024-06-12 | 5 | 55000 | 500% | 13750 | 261250 | 31350 | 292600 | 30 Days Net | IT Manager | ✅ Closed | Color MFP rollout
PO-2024-041 | SUP-030 | Pacific Paint (Boysen) Philippines Inc. | Construction Materials | Boysen Skim Coat 25kg (bag) | 2024-06-10 | 2024-06-15 | 500 | 420 | 0% | 0 | 210000 | 25200 | 235200 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A - Finishing
PO-2024-042 | SUP-031 | Davies Paints Philippines Inc. | Construction Materials | Davies Weathercoat Exterior Paint 4L | 2024-06-12 | 2024-06-17 | 400 | 680 | 0% | 0 | 272000 | 32640 | 304640 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A - Exterior
PO-2024-043 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial Grade, liters) | 2024-06-25 | 2024-06-28 | 15000 | 70.8 | 0% | 0 | 1062000 | 127440 | 1189440 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Jun
PO-2024-044 | SUP-023 | National Book Store Inc. | Office Supplies | Bond Paper Legal 80gsm (ream) | 2024-07-01 | 2024-07-04 | 150 | 285 | 0% | 0 | 42750 | 5130 | 47880 | 30 Days Net | Admin Officer | ✅ Closed | Q3 office supply
PO-2024-045 | SUP-002 | Republic Cement & Building Materials Inc. | Cement & Concrete | Republic Cement Premium OPC 40kg | 2024-07-05 | 2024-07-15 | 3500 | 292 | 200% | 20440 | 1001560 | 120187.2 | 1121747.2 | 45 Days Net | VP-Operations | ✅ Closed | Site B - 3F slab
PO-2024-046 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Wire Mesh 4mm x 100mm (2.4x6m) | 2024-07-08 | 2024-07-22 | 2000 | 1850 | 150% | 55500 | 3644500 | 437340 | 4081840 | 30 Days Net | VP-Operations | ✅ Closed | Slab reinforcement
PO-2024-047 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB Transformer 500kVA 13.8kV/400V | 2024-07-10 | 2024-07-24 | 1 | 1850000 | 300% | 55500 | 1794500 | 215340 | 2009840 | 30 Days Net | CEO | ✅ Closed | Site B main transformer
PO-2024-048 | SUP-008 | Ace Hardware Philippines Inc. | Hardware & Tools | Grinding Disc 4.5in (box of 25) | 2024-07-15 | 2024-07-18 | 80 | 1250 | 0% | 0 | 100000 | 12000 | 112000 | 30 Days Net | Procurement Mgr | ✅ Closed | Steel cutting works
PO-2024-049 | SUP-008 | Ace Hardware Philippines Inc. | Hardware & Tools | Cut-off Disc 14in (box of 10) | 2024-07-15 | 2024-07-18 | 40 | 2100 | 0% | 0 | 84000 | 10080 | 94080 | 30 Days Net | Procurement Mgr | ✅ Closed | Steel cutting works
PO-2024-050 | SUP-027 | Meralco (Manila Electric Company) | Utilities | Meralco Temporary Power Connection Fee | 2024-07-20 | 2024-08-20 | 1 | 185000 | 0% | 0 | 185000 | 22200 | 207200 | 30 Days Net | VP-Operations | ✅ Closed | Site B power connection
PO-2024-051 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2024-07-25 | 2024-07-28 | 12000 | 71.5 | 0% | 0 | 858000 | 102960 | 960960 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Jul
PO-2024-052 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider EasyPact MVS 800A ACB | 2024-08-02 | 2024-08-16 | 4 | 285000 | 300% | 34200 | 1105800 | 132696 | 1238496 | 45 Days Net | VP-Operations | ✅ Closed | Main switchboard
PO-2024-053 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Safety Goggles GoggleGear 500 | 2024-08-05 | 2024-08-12 | 250 | 480 | 0% | 0 | 120000 | 14400 | 134400 | 30 Days Net | Safety Officer | ✅ Closed | Eye protection renewal
PO-2024-054 | SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | CEMEX Ready Mix Concrete 3000 PSI (m3) | 2024-08-08 | 2024-08-15 | 500 | 5200 | 0% | 0 | 2600000 | 312000 | 2912000 | 30 Days Net | VP-Operations | ✅ Closed | Site C - Foundation pour
PO-2024-055 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Crushed Gravel 1.5 inch (cubic meter) | 2024-08-10 | 2024-08-17 | 200 | 2400 | 0% | 0 | 480000 | 57600 | 537600 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C sub-base
PO-2024-056 | SUP-019 | Dell Technologies Philippines | IT Equipment | Dell PowerEdge R750 Server | 2024-08-15 | 2024-08-22 | 2 | 385000 | 500% | 38500 | 731500 | 87780 | 819280 | 30 Days Net | IT Manager | ✅ Closed | Data center upgrade
PO-2024-057 | SUP-023 | National Book Store Inc. | Office Supplies | Toner Cartridge HP 85A (box of 6) | 2024-08-20 | 2024-08-23 | 20 | 8500 | 0% | 0 | 170000 | 20400 | 190400 | 30 Days Net | Admin Officer | ✅ Closed | Printers consumables
PO-2024-058 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2024-08-25 | 2024-08-28 | 18000 | 71.8 | 0% | 0 | 1292400 | 155088 | 1447488 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Aug
PO-2024-059 | SUP-005 | Capital Steel Corporation | Steel & Metal | Steel H-Beam 200x200mm (12m) | 2024-09-03 | 2024-09-17 | 200 | 12500 | 200% | 50000 | 2450000 | 294000 | 2744000 | 45 Days Net | VP-Operations | ✅ Closed | Site C - Structural frame
PO-2024-060 | SUP-035 | EEI Corporation | Engineering Services | EEI Civil Works - Site C Foundation | 2024-09-05 | 2024-10-05 | 1 | 12500000 | 0% | 0 | 12500000 | 1500000 | 14000000 | 30 Days Net | CEO | ✅ Closed | Subcontract Site C
PO-2024-061 | SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Waterproofing Compound 25L | 2024-09-08 | 2024-09-15 | 200 | 1850 | 0% | 0 | 370000 | 44400 | 414400 | 30 Days Net | Procurement Mgr | ✅ Closed | Site B basement waterproof
PO-2024-062 | SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Epoxy Floor Coating 4L | 2024-09-08 | 2024-09-15 | 100 | 3200 | 0% | 0 | 320000 | 38400 | 358400 | 30 Days Net | Procurement Mgr | ✅ Closed | Site A parking level
PO-2024-063 | SUP-014 | Honeywell Philippines Inc. | Safety Equipment | Honeywell Fall Arrest Harness | 2024-09-10 | 2024-09-17 | 80 | 3500 | 0% | 0 | 280000 | 33600 | 313600 | 45 Days Net | Safety Officer | ✅ Closed | High-rise PPE Site C
PO-2024-064 | SUP-025 | PLDT Inc. | Telecommunications | PLDT Fiber Business Internet 1Gbps (12mo) | 2024-09-15 | 2024-10-15 | 1 | 85000 | 0% | 0 | 85000 | 10200 | 95200 | 30 Days Net | IT Manager | ✅ Closed | Site office connectivity
PO-2024-065 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2024-09-25 | 2024-09-28 | 20000 | 72.1 | 0% | 0 | 1442000 | 173040 | 1615040 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Sep
PO-2024-066 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido Mastercem OPC 40kg | 2024-10-04 | 2024-10-11 | 4000 | 295 | 200% | 23600 | 1156400 | 138768 | 1295168 | 30 Days Net | VP-Operations | ✅ Closed | Site C - 2F works
PO-2024-067 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 25mm x 6m (High Tensile) | 2024-10-07 | 2024-10-21 | 1000 | 1050 | 200% | 21000 | 1029000 | 123480 | 1152480 | 30 Days Net | VP-Operations | ✅ Closed | Site C columns
PO-2024-068 | SUP-029 | Lafarge Republic Inc. | Cement & Concrete | Lafarge Aircem Masonry Cement 40kg | 2024-10-10 | 2024-10-20 | 2000 | 305 | 100% | 6100 | 603900 | 72468 | 676368 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C - Block walls
PO-2024-069 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB ACS580 VFD 55kW Drive | 2024-10-14 | 2024-10-28 | 6 | 185000 | 300% | 33300 | 1076700 | 129204 | 1205904 | 30 Days Net | VP-Operations | ✅ Closed | HVAC drives Site B
PO-2024-070 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Hollow Blocks 4-inch (pieces) | 2024-10-17 | 2024-10-20 | 20000 | 18 | 0% | 0 | 360000 | 43200 | 403200 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C - Block works
PO-2024-071 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Hollow Blocks 6-inch (pieces) | 2024-10-17 | 2024-10-20 | 15000 | 24 | 0% | 0 | 360000 | 43200 | 403200 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C - Block works
PO-2024-072 | SUP-022 | Epson Philippines Corporation | IT Equipment | Epson EcoTank L15150 A3 Printer | 2024-10-20 | 2024-10-27 | 4 | 45000 | 500% | 9000 | 171000 | 20520 | 191520 | 30 Days Net | IT Manager | ✅ Closed | Engineering dept printers
PO-2024-073 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (liters) | 2024-10-25 | 2024-10-28 | 18000 | 73.5 | 0% | 0 | 1323000 | 158760 | 1481760 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Oct
PO-2024-074 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Safety Boot Steel Toe Size 7-11 | 2024-11-04 | 2024-11-11 | 120 | 2850 | 0% | 0 | 342000 | 41040 | 383040 | 30 Days Net | Safety Officer | ✅ Closed | Annual PPE replacement
PO-2024-075 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider Acti9 iC60H 40A MCB | 2024-11-07 | 2024-11-21 | 300 | 485 | 500% | 7275 | 138225 | 16587 | 154812 | 45 Days Net | VP-Operations | ✅ Closed | Sub-distribution boards
PO-2024-076 | SUP-030 | Pacific Paint (Boysen) Philippines Inc. | Construction Materials | Boysen Acrytex Primer 4L | 2024-11-10 | 2024-11-15 | 300 | 650 | 0% | 0 | 195000 | 23400 | 218400 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C - Interior prep
PO-2024-077 | SUP-032 | Neltex Development Co. Inc. | Construction Materials | uPVC Pipe 3 inch x 6m (S-1000) | 2024-11-12 | 2024-11-19 | 400 | 320 | 0% | 0 | 128000 | 15360 | 143360 | 30 Days Net | Procurement Mgr | ✅ Closed | Drainage works Site C
PO-2024-078 | SUP-036 | Sta. Clara International Corporation | Engineering Services | Sta. Clara MEP Installation - Site B | 2024-11-15 | 2024-12-15 | 1 | 8500000 | 0% | 0 | 8500000 | 1020000 | 9520000 | 30 Days Net | CEO | ✅ Closed | Subcontract MEP works
PO-2024-079 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2024-11-25 | 2024-11-28 | 20000 | 73.8 | 0% | 0 | 1476000 | 177120 | 1653120 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Nov
PO-2024-080 | SUP-023 | National Book Store Inc. | Office Supplies | Office Furniture Ergonomic Chair (set) | 2024-11-27 | 2024-11-30 | 20 | 8500 | 500% | 8500 | 161500 | 19380 | 180880 | 30 Days Net | Admin Manager | ✅ Closed | New office fit-out
PO-2024-081 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Portland Cement Type I (40kg bag) | 2024-12-03 | 2024-12-10 | 5000 | 298 | 200% | 29800 | 1460200 | 175224 | 1635424 | 30 Days Net | VP-Operations | ✅ Closed | Site C - Year-end push
PO-2024-082 | SUP-018 | HP Philippines Inc. | IT Equipment | HP EliteBook 840 G11 Laptop | 2024-12-05 | 2024-12-12 | 10 | 95000 | 500% | 47500 | 902500 | 108300 | 1010800 | 30 Days Net | IT Manager | ✅ Closed | Management laptops
PO-2024-083 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Washed Sand (cubic meter) | 2024-12-07 | 2024-12-14 | 400 | 1850 | 0% | 0 | 740000 | 88800 | 828800 | 30 Days Net | Procurement Mgr | ✅ Closed | Year-end stockpile
PO-2024-084 | SUP-026 | Globe Telecom Inc. | Telecommunications | Globe One Business Postpaid 50 lines | 2024-12-10 | 2025-01-10 | 1 | 125000 | 0% | 0 | 125000 | 15000 | 140000 | 30 Days Net | Admin Manager | ✅ Closed | Employee mobile plans
PO-2024-085 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2024-12-23 | 2024-12-26 | 22000 | 74.2 | 0% | 0 | 1632400 | 195888 | 1828288 | 15 Days Net | Admin Manager | ✅ Closed | Equipment fuel Dec
PO-2025-001 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2025-01-06 | 2025-01-13 | 4500 | 302 | 200% | 27180 | 1331820 | 159818.4 | 1491638.4 | 30 Days Net | VP-Operations | ✅ Closed | Site C - 3F column
PO-2025-002 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 32mm x 6m | 2025-01-08 | 2025-01-22 | 800 | 1650 | 200% | 26400 | 1293600 | 155232 | 1448832 | 30 Days Net | VP-Operations | ✅ Closed | Site C - Transfer beam
PO-2025-003 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M 8210 N95 Respirator (box of 20) | 2025-01-10 | 2025-01-17 | 100 | 1850 | 0% | 0 | 185000 | 22200 | 207200 | 30 Days Net | Safety Officer | ✅ Closed | Annual PPE restocking
PO-2025-004 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider Prisma Plus G Panel 1600A | 2025-01-15 | 2025-01-29 | 2 | 385000 | 500% | 38500 | 731500 | 87780 | 819280 | 45 Days Net | VP-Operations | ✅ Closed | Main LV panel Site C
PO-2025-005 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-01-23 | 2025-01-26 | 20000 | 74.8 | 0% | 0 | 1496000 | 179520 | 1675520 | 15 Days Net | Admin Manager | ✅ Closed | Jan 2025 equipment fuel
PO-2025-006 | SUP-023 | National Book Store Inc. | Office Supplies | Bond Paper A4 80gsm (ream) | 2025-01-27 | 2025-01-30 | 300 | 278 | 0% | 0 | 83400 | 10008 | 93408 | 30 Days Net | Admin Officer | ✅ Closed | Q1 2025 office supply
PO-2025-007 | SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | CEMEX OPC Premium Blend 40kg | 2025-02-04 | 2025-02-11 | 3000 | 298 | 200% | 17880 | 876120 | 105134.4 | 981254.4 | 30 Days Net | VP-Operations | ✅ Closed | Site C - 3F slab
PO-2025-008 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Crushed Gravel 3/4 inch (cubic meter) | 2025-02-06 | 2025-02-13 | 300 | 2250 | 0% | 0 | 675000 | 81000 | 756000 | 30 Days Net | Procurement Mgr | ✅ Closed | Backfill works Site C
PO-2025-009 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB ACS880 Drive 110kW Industrial | 2025-02-10 | 2025-02-24 | 3 | 485000 | 300% | 43650 | 1411350 | 169362 | 1580712 | 30 Days Net | VP-Operations | ✅ Closed | Pump stations
PO-2025-010 | SUP-037 | Komatsu Philippines Inc. | Heavy Equipment | Komatsu WA380-8 Wheel Loader | 2025-02-14 | 2025-03-14 | 1 | 12500000 | 0% | 0 | 12500000 | 1500000 | 14000000 | 45 Days Net | CEO | ✅ Closed | Site D capital equipment
PO-2025-011 | SUP-005 | Capital Steel Corporation | Steel & Metal | Steel Wide Flange W250x89 (12m) | 2025-02-18 | 2025-03-04 | 300 | 18500 | 200% | 111000 | 5439000 | 652680 | 6091680 | 45 Days Net | VP-Operations | ✅ Closed | Site C - Steel frame
PO-2025-012 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-02-24 | 2025-02-27 | 22000 | 75.5 | 0% | 0 | 1661000 | 199320 | 1860320 | 15 Days Net | Admin Manager | ✅ Closed | Feb 2025 fuel
PO-2025-013 | SUP-019 | Dell Technologies Philippines | IT Equipment | Dell Latitude 5550 Laptop | 2025-03-03 | 2025-03-10 | 20 | 58000 | 500% | 58000 | 1102000 | 132240 | 1234240 | 30 Days Net | IT Manager | ✅ Closed | Site engineer laptops
PO-2025-014 | SUP-032 | Neltex Development Co. Inc. | Construction Materials | Neltex uPVC Pipe 2 inch x 6m | 2025-03-05 | 2025-03-12 | 600 | 220 | 0% | 0 | 132000 | 15840 | 147840 | 30 Days Net | Procurement Mgr | ✅ Closed | Water supply roughing
PO-2025-015 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider Easergy T200P Protection Relay | 2025-03-08 | 2025-03-22 | 10 | 125000 | 500% | 62500 | 1187500 | 142500 | 1330000 | 45 Days Net | VP-Operations | ✅ Closed | Substation relays
PO-2025-016 | SUP-035 | EEI Corporation | Engineering Services | EEI Structural Works - Site D | 2025-03-12 | 2025-04-12 | 1 | 28500000 | 0% | 0 | 28500000 | 3420000 | 31920000 | 30 Days Net | CEO | 🔄 Ongoing | Major subcontract Site D
PO-2025-017 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M DBI-SALA Roofing Anchor | 2025-03-17 | 2025-03-24 | 60 | 8500 | 0% | 0 | 510000 | 61200 | 571200 | 30 Days Net | Safety Officer | ✅ Closed | Roofing PPE Site C
PO-2025-018 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-03-25 | 2025-03-28 | 25000 | 75.1 | 0% | 0 | 1877500 | 225300 | 2102800 | 15 Days Net | Admin Manager | ✅ Closed | Mar 2025 fuel
PO-2025-019 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim HiEarly Cement 40kg | 2025-04-01 | 2025-04-08 | 5000 | 315 | 200% | 31500 | 1543500 | 185220 | 1728720 | 30 Days Net | VP-Operations | ✅ Closed | Site D - Foundation pour
PO-2025-020 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 12mm x 6m (Seismic) | 2025-04-03 | 2025-04-17 | 6000 | 295 | 200% | 35400 | 1734600 | 208152 | 1942752 | 30 Days Net | VP-Operations | ✅ Closed | Site D - Seismic zone
PO-2025-021 | SUP-029 | Lafarge Republic Inc. | Cement & Concrete | Lafarge Wallmax Masonry Cement 40kg | 2025-04-07 | 2025-04-17 | 2500 | 312 | 100% | 7800 | 772200 | 92664 | 864864 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - CHB laying
PO-2025-022 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Hollow Blocks 6-inch (pieces) | 2025-04-10 | 2025-04-13 | 30000 | 25 | 0% | 0 | 750000 | 90000 | 840000 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - Block works
PO-2025-023 | SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Sika 212 Crystalline Waterproofing 25kg | 2025-04-12 | 2025-04-19 | 250 | 2200 | 0% | 0 | 550000 | 66000 | 616000 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D basement
PO-2025-024 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-04-24 | 2025-04-27 | 28000 | 76.2 | 0% | 0 | 2133600 | 256032 | 2389632 | 15 Days Net | Admin Manager | ✅ Closed | Apr 2025 fuel
PO-2025-025 | SUP-010 | Siemens Philippines Inc. | Electrical & Mechanical | Siemens HV/LV Transformer 1000kVA | 2025-05-05 | 2025-05-26 | 1 | 3850000 | 500% | 192500 | 3657500 | 438900 | 4096400 | 45 Days Net | CEO | ✅ Closed | Site D main transformer
PO-2025-026 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Washed Sand (cubic meter) | 2025-05-08 | 2025-05-15 | 500 | 1900 | 0% | 0 | 950000 | 114000 | 1064000 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D mortar works
PO-2025-027 | SUP-006 | Peerless Metal Industries Inc. | Steel & Metal | Corrugated GI Roof Sheet G24 (5m) | 2025-05-12 | 2025-05-22 | 1200 | 680 | 0% | 0 | 816000 | 97920 | 913920 | 30 Days Net | Procurement Mgr | ✅ Closed | Site C - Roof completion
PO-2025-028 | SUP-023 | National Book Store Inc. | Office Supplies | Epson 003 Ink Bottle Set (4-color) | 2025-05-14 | 2025-05-17 | 80 | 850 | 0% | 0 | 68000 | 8160 | 76160 | 30 Days Net | Admin Officer | ✅ Closed | Printer consumables
PO-2025-029 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M WorkTunes Wireless Hearing Protector | 2025-05-16 | 2025-05-23 | 100 | 3850 | 0% | 0 | 385000 | 46200 | 431200 | 30 Days Net | Safety Officer | ✅ Closed | Noise area works Site D
PO-2025-030 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-05-26 | 2025-05-29 | 30000 | 76.8 | 0% | 0 | 2304000 | 276480 | 2580480 | 15 Days Net | Admin Manager | ✅ Closed | May 2025 fuel
PO-2025-031 | SUP-012 | Legrand Philippines Inc. | Electrical & Mechanical | Legrand Trunking 100x50mm (2m) | 2025-06-03 | 2025-06-13 | 800 | 485 | 500% | 19400 | 368600 | 44232 | 412832 | 30 Days Net | VP-Operations | ✅ Closed | Cable management Site D
PO-2025-032 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB SACE E2.2 2000A ACB 3P | 2025-06-05 | 2025-06-19 | 2 | 1250000 | 300% | 75000 | 2425000 | 291000 | 2716000 | 30 Days Net | VP-Operations | ✅ Closed | HV room Site D
PO-2025-033 | SUP-018 | HP Philippines Inc. | IT Equipment | HP ProOne 440 G9 AIO PC | 2025-06-09 | 2025-06-16 | 25 | 55000 | 500% | 68750 | 1306250 | 156750 | 1463000 | 30 Days Net | IT Manager | ✅ Closed | Project management office
PO-2025-034 | SUP-038 | Volvo Financial Services Philippines | Heavy Equipment | Volvo EC380E Crawler Excavator | 2025-06-12 | 2025-07-12 | 1 | 22500000 | 0% | 0 | 22500000 | 2700000 | 25200000 | 60 Days Net | CEO | 🔄 Ongoing | Site D - major earthworks
PO-2025-035 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-06-25 | 2025-06-28 | 30000 | 77.5 | 0% | 0 | 2325000 | 279000 | 2604000 | 15 Days Net | Admin Manager | ✅ Closed | Jun 2025 fuel
PO-2025-036 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2025-07-01 | 2025-07-08 | 6000 | 308 | 200% | 36960 | 1811040 | 217324.8 | 2028364.8 | 30 Days Net | VP-Operations | ✅ Closed | Site D - 2F concrete
PO-2025-037 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 16mm x 6m (BIS) | 2025-07-04 | 2025-07-18 | 4000 | 510 | 150% | 30600 | 2009400 | 241128 | 2250528 | 30 Days Net | VP-Operations | ✅ Closed | Site D - Beams
PO-2025-038 | SUP-036 | Sta. Clara International Corporation | Engineering Services | Sta. Clara HVAC Installation - Site D | 2025-07-07 | 2025-08-07 | 1 | 15800000 | 0% | 0 | 15800000 | 1896000 | 17696000 | 30 Days Net | CEO | 🔄 Ongoing | HVAC full package
PO-2025-039 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Safety Boot Steel Toe (pairs) | 2025-07-10 | 2025-07-17 | 200 | 2950 | 0% | 0 | 590000 | 70800 | 660800 | 30 Days Net | Safety Officer | ✅ Closed | Mid-year PPE replacement
PO-2025-040 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-07-28 | 2025-07-31 | 32000 | 77.1 | 0% | 0 | 2467200 | 296064 | 2763264 | 15 Days Net | Admin Manager | ✅ Closed | Jul 2025 fuel
PO-2025-041 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider Altivar 630 VFD 185kW | 2025-08-04 | 2025-08-18 | 4 | 850000 | 500% | 170000 | 3230000 | 387600 | 3617600 | 45 Days Net | VP-Operations | ✅ Closed | Chiller drives Site D
PO-2025-042 | SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | CEMEX Ready Mix 4000 PSI (m3) | 2025-08-06 | 2025-08-13 | 800 | 5500 | 0% | 0 | 4400000 | 528000 | 4928000 | 30 Days Net | VP-Operations | ✅ Closed | Site D - High-strength slab
PO-2025-043 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Crushed Gravel 3/4 inch (cubic meter) | 2025-08-08 | 2025-08-15 | 400 | 2300 | 0% | 0 | 920000 | 110400 | 1030400 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D sub-base
PO-2025-044 | SUP-019 | Dell Technologies Philippines | IT Equipment | Dell UltraSharp U2724D Monitor 27in | 2025-08-12 | 2025-08-19 | 30 | 32000 | 500% | 48000 | 912000 | 109440 | 1021440 | 30 Days Net | IT Manager | ✅ Closed | Engineer workstations
PO-2025-045 | SUP-030 | Pacific Paint (Boysen) Philippines Inc. | Construction Materials | Boysen Permacoat Latex White 4L | 2025-08-15 | 2025-08-20 | 600 | 598 | 0% | 0 | 358800 | 43056 | 401856 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - Interior painting
PO-2025-046 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-08-27 | 2025-08-30 | 35000 | 78.2 | 0% | 0 | 2737000 | 328440 | 3065440 | 15 Days Net | Admin Manager | ✅ Closed | Aug 2025 fuel
PO-2025-047 | SUP-029 | Lafarge Republic Inc. | Cement & Concrete | Lafarge HiStrength Cement 40kg | 2025-09-02 | 2025-09-12 | 3000 | 325 | 100% | 9750 | 965250 | 115830 | 1081080 | 30 Days Net | VP-Operations | ✅ Closed | Site D - Special concrete
PO-2025-048 | SUP-005 | Capital Steel Corporation | Steel & Metal | Steel C-Channel 150x65mm (6m) | 2025-09-05 | 2025-09-19 | 1500 | 620 | 100% | 9300 | 920700 | 110484 | 1031184 | 45 Days Net | VP-Operations | ✅ Closed | Site D - Secondary framing
PO-2025-049 | SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Sika 101A Waterproofing Mortar 25kg | 2025-09-09 | 2025-09-16 | 300 | 1950 | 0% | 0 | 585000 | 70200 | 655200 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - Roof deck
PO-2025-050 | SUP-023 | National Book Store Inc. | Office Supplies | Stapler Heavy Duty & Staples Set | 2025-09-11 | 2025-09-14 | 30 | 1250 | 0% | 0 | 37500 | 4500 | 42000 | 30 Days Net | Admin Officer | ✅ Closed | Q3 2025 office supply
PO-2025-051 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-09-26 | 2025-09-29 | 32000 | 78.5 | 0% | 0 | 2512000 | 301440 | 2813440 | 15 Days Net | Admin Manager | ✅ Closed | Sep 2025 fuel
PO-2025-052 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB Relion 670 Series Protection IED | 2025-10-06 | 2025-10-20 | 5 | 285000 | 300% | 42750 | 1382250 | 165870 | 1548120 | 30 Days Net | VP-Operations | ✅ Closed | Substation protection
PO-2025-053 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2025-10-08 | 2025-10-15 | 7000 | 312 | 200% | 43680 | 2140320 | 256838.4 | 2397158.4 | 30 Days Net | VP-Operations | ✅ Closed | Site D - 4F & 5F
PO-2025-054 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 20mm x 6m | 2025-10-10 | 2025-10-24 | 3000 | 720 | 200% | 43200 | 2116800 | 254016 | 2370816 | 30 Days Net | VP-Operations | ✅ Closed | Site D - Girder system
PO-2025-055 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Ceramic Floor Tile 60x60cm (box) | 2025-10-13 | 2025-10-16 | 2000 | 1850 | 0% | 0 | 3700000 | 444000 | 4144000 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - Finishing works
PO-2025-056 | SUP-007 | Wilcon Depot Inc. | Hardware & Tools | Wall Tile 30x60cm Matte (box) | 2025-10-13 | 2025-10-16 | 1500 | 1650 | 0% | 0 | 2475000 | 297000 | 2772000 | 30 Days Net | Procurement Mgr | ✅ Closed | Site D - Finishing works
PO-2025-057 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-10-28 | 2025-10-31 | 35000 | 79.1 | 0% | 0 | 2768500 | 332220 | 3100720 | 15 Days Net | Admin Manager | ✅ Closed | Oct 2025 fuel
PO-2025-058 | SUP-020 | Lenovo Philippines | IT Equipment | Lenovo ThinkCentre M70q Gen5 Mini PC | 2025-11-03 | 2025-11-10 | 15 | 42000 | 500% | 31500 | 598500 | 71820 | 670320 | 30 Days Net | IT Manager | ✅ Closed | Admin department upgrade
PO-2025-059 | SUP-014 | Honeywell Philippines Inc. | Safety Equipment | Honeywell BW Ultra Portable Gas Detector | 2025-11-05 | 2025-11-12 | 30 | 28500 | 0% | 0 | 855000 | 102600 | 957600 | 45 Days Net | Safety Officer | ✅ Closed | Gas detection upgrade
PO-2025-060 | SUP-035 | EEI Corporation | Engineering Services | EEI Structural Steel Erection - Site D | 2025-11-08 | 2025-12-08 | 1 | 18500000 | 0% | 0 | 18500000 | 2220000 | 20720000 | 30 Days Net | CEO | 🔄 Ongoing | Steel erection contract
PO-2025-061 | SUP-031 | Davies Paints Philippines Inc. | Construction Materials | Davies Firecheck Intumescent Paint 4L | 2025-11-10 | 2025-11-15 | 400 | 1250 | 0% | 0 | 500000 | 60000 | 560000 | 30 Days Net | Procurement Mgr | ✅ Closed | Fire protection coating
PO-2025-062 | SUP-032 | Neltex Development Co. Inc. | Construction Materials | Neltex uPVC Fittings Assorted Set | 2025-11-12 | 2025-11-19 | 1000 | 180 | 0% | 0 | 180000 | 21600 | 201600 | 30 Days Net | Procurement Mgr | ✅ Closed | Plumbing Site D
PO-2025-063 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-11-27 | 2025-11-30 | 35000 | 79.8 | 0% | 0 | 2793000 | 335160 | 3128160 | 15 Days Net | Admin Manager | ✅ Closed | Nov 2025 fuel
PO-2025-064 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Virtua CCS Safety Glasses (box of 20) | 2025-12-01 | 2025-12-08 | 50 | 2200 | 0% | 0 | 110000 | 13200 | 123200 | 30 Days Net | Safety Officer | ✅ Closed | Year-end PPE
PO-2025-065 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider Galaxy VS UPS 80kVA | 2025-12-03 | 2025-12-17 | 2 | 1850000 | 500% | 185000 | 3515000 | 421800 | 3936800 | 45 Days Net | CEO | ✅ Closed | Data center UPS Site D
PO-2025-066 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2025-12-05 | 2025-12-12 | 8000 | 318 | 200% | 50880 | 2493120 | 299174.4 | 2792294.4 | 30 Days Net | VP-Operations | ✅ Closed | Site D - 6F push
PO-2025-067 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Washed Sand (cubic meter) | 2025-12-08 | 2025-12-15 | 500 | 1950 | 0% | 0 | 975000 | 117000 | 1092000 | 30 Days Net | Procurement Mgr | ✅ Closed | Year-end stockpile
PO-2025-068 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2025-12-26 | 2025-12-29 | 40000 | 80.5 | 0% | 0 | 3220000 | 386400 | 3606400 | 15 Days Net | Admin Manager | ✅ Closed | Dec 2025 fuel
PO-2026-001 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2026-01-05 | 2026-01-12 | 8000 | 322 | 200% | 51520 | 2524480 | 302937.6 | 2827417.6 | 30 Days Net | VP-Operations | 📋 Received | Site D - 7F works
PO-2026-002 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 25mm x 6m | 2026-01-07 | 2026-01-21 | 2500 | 1100 | 200% | 55000 | 2695000 | 323400 | 3018400 | 30 Days Net | VP-Operations | 📋 Received | Site D - Roof level
PO-2026-003 | SUP-009 | Schneider Electric Philippines Inc. | Electrical & Mechanical | Schneider PM8000 Power Quality Meter | 2026-01-10 | 2026-01-24 | 8 | 185000 | 500% | 74000 | 1406000 | 168720 | 1574720 | 45 Days Net | VP-Operations | 📋 Received | Energy mgmt system
PO-2026-004 | SUP-019 | Dell Technologies Philippines | IT Equipment | Dell Vostro 3530 Business Laptop | 2026-01-13 | 2026-01-20 | 25 | 38000 | 500% | 47500 | 902500 | 108300 | 1010800 | 30 Days Net | IT Manager | 📋 Received | Site D project office
PO-2026-005 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M PPE Kit (Full Set per person) | 2026-01-15 | 2026-01-22 | 150 | 4850 | 0% | 0 | 727500 | 87300 | 814800 | 30 Days Net | Safety Officer | 📋 Received | Site D full crew PPE
PO-2026-006 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2026-01-27 | 2026-01-30 | 40000 | 81.2 | 0% | 0 | 3248000 | 389760 | 3637760 | 15 Days Net | Admin Manager | 📋 Received | Jan 2026 fuel
PO-2026-007 | SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | Sika Monotop 612 Repair Mortar 25kg | 2026-02-03 | 2026-02-10 | 200 | 2850 | 0% | 0 | 570000 | 68400 | 638400 | 30 Days Net | Procurement Mgr | 📝 Ordered | Concrete repair works
PO-2026-008 | SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | Crushed Gravel 3/4 inch (cubic meter) | 2026-02-05 | 2026-02-12 | 500 | 2380 | 0% | 0 | 1190000 | 142800 | 1332800 | 30 Days Net | Procurement Mgr | 📝 Ordered | Site E - Pre-earthworks
PO-2026-009 | SUP-035 | EEI Corporation | Engineering Services | EEI Piling Works - Site E | 2026-02-10 | 2026-03-10 | 1 | 35000000 | 0% | 0 | 35000000 | 4200000 | 39200000 | 30 Days Net | CEO | 📝 Ordered | New project Site E
PO-2026-010 | SUP-003 | CEMEX Holdings Philippines Inc. | Cement & Concrete | CEMEX OPC Bulk Cement (metric ton) | 2026-02-13 | 2026-02-20 | 500 | 7800 | 0% | 0 | 3900000 | 468000 | 4368000 | 30 Days Net | VP-Operations | 📝 Ordered | Site E - Piling concrete
PO-2026-011 | SUP-016 | Shell Philippines Exploration B.V. | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2026-02-25 | 2026-02-28 | 45000 | 82.1 | 0% | 0 | 3694500 | 443340 | 4137840 | 15 Days Net | Admin Manager | 📝 Ordered | Feb 2026 fuel
PO-2026-012 | SUP-038 | Volvo Financial Services Philippines | Heavy Equipment | Volvo A45G Articulated Hauler | 2026-03-03 | 2026-04-03 | 2 | 28500000 | 0% | 0 | 57000000 | 6840000 | 63840000 | 60 Days Net | CEO | 📝 Ordered | Site E - Earthworks fleet
PO-2026-013 | SUP-010 | Siemens Philippines Inc. | Electrical & Mechanical | Siemens SIMATIC S7-1500 PLC System | 2026-03-05 | 2026-03-26 | 3 | 850000 | 500% | 127500 | 2422500 | 290700 | 2713200 | 45 Days Net | VP-Operations | 📝 Ordered | Site D automation
PO-2026-014 | SUP-036 | Sta. Clara International Corporation | Engineering Services | Sta. Clara Plumbing Works - Site D | 2026-03-08 | 2026-04-08 | 1 | 12500000 | 0% | 0 | 12500000 | 1500000 | 14000000 | 30 Days Net | CEO | 📝 Ordered | Plumbing completion
PO-2026-015 | SUP-013 | 3M Philippines Inc. | Safety Equipment | 3M Versaflo TR-300 PAPR | 2026-03-12 | 2026-03-19 | 40 | 28500 | 0% | 0 | 1140000 | 136800 | 1276800 | 30 Days Net | Safety Officer | 📝 Ordered | High-dust works Site E
PO-2026-016 | SUP-023 | National Book Store Inc. | Office Supplies | Office Supplies Quarterly Bundle | 2026-03-14 | 2026-03-17 | 1 | 85000 | 0% | 0 | 85000 | 10200 | 95200 | 30 Days Net | Admin Manager | 📝 Ordered | Q1 2026 bulk order
PO-2026-017 | SUP-015 | Petron Corporation | Fuel & Lubricants | Diesel Fuel (Industrial liters) | 2026-03-27 | 2026-03-30 | 48000 | 82.8 | 0% | 0 | 3974400 | 476928 | 4451328 | 15 Days Net | Admin Manager | 📝 Ordered | Mar 2026 fuel
PO-2026-018 | SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | Deformed Steel Bar 12mm x 6m | 2026-04-01 | 2026-04-15 | 8000 | 305 | 200% | 48800 | 2391200 | 286944 | 2678144 | 30 Days Net | VP-Operations | 📝 Ordered | Site E - Foundation rebar
PO-2026-019 | SUP-001 | Holcim Philippines Inc. | Cement & Concrete | Holcim Solido OPC 40kg | 2026-04-03 | 2026-04-10 | 10000 | 325 | 200% | 65000 | 3185000 | 382200 | 3567200 | 30 Days Net | VP-Operations | 📝 Ordered | Site E - Foundation
PO-2026-020 | SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | ABB SafeRing 24kV RMU | 2026-04-07 | 2026-04-21 | 2 | 2850000 | 300% | 171000 | 5529000 | 663480 | 6192480 | 30 Days Net | CEO | 📝 Ordered | Site E MV switchgear
TOTAL PURCHASE ORDERS VALUE | [10 empty] | 417522460 | 50102695.2 | 467625155.2

## Goods Receipt Log
📦 Pinnacle Construction & Development Corporation — GOODS RECEIPT & INSPECTION LOG
Receiving & Quality Inspection Records · Warehouse Division · 2024–2026
GR Number | PO Reference | Supplier | Item Description | PO Qty | Received Qty | Variance | Receive Date | Received By | Inspection Result | Inspected By | Condition | Location | Remarks
GR-2024-001 | PO-2024-001 | Holcim Philippines Inc. | Portland Cement Type I (40kg bag) | 2000 | 2000 | 0 | 2024-01-15 | Warehouse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site A - Bodega 1 | Full delivery
GR-2024-002 | PO-2024-002 | SteelAsia Manufacturing | Deformed Steel Bar 10mm x 6m | 5000 | 5000 | 0 | 2024-01-24 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site A - Steel Yard | MTR received
GR-2024-003 | PO-2024-003 | SteelAsia Manufacturing | Deformed Steel Bar 12mm x 6m | 3000 | 2800 | -200 | 2024-01-24 | Warehse Keeper R. Dela Cruz | ⚠ Partial | QC Inspector A. Reyes | Good Condition | Site A - Steel Yard | Shortage 200pcs — backorder issued
GR-2024-004 | PO-2024-004 | Wilcon Depot Inc. | Plywood Marine 1/2 inch (4x8ft) | 500 | 500 | 0 | 2024-01-18 | Warehse Keeper M. Santos | ✅ Passed | QC Inspector B. Tan | Good Condition | Site A - Bodega 2 | Complete delivery
GR-2024-005 | PO-2024-005 | Schneider Electric PH | Circuit Breaker 100A 3-Phase MCCB | 50 | 50 | 0 | 2024-02-01 | Warehse Keeper M. Santos | ✅ Passed | QC Inspector A. Reyes | Good Condition | Electrical Room Store | With test certs
GR-2024-006 | PO-2024-006 | 3M Philippines Inc. | Safety Helmet (ANSI Z89.1) | 200 | 200 | 0 | 2024-01-27 | Safety Officer J. Cruz | ✅ Passed | Safety Officer J. Cruz | Good Condition | PPE Storage Room | Batch number recorded
GR-2024-007 | PO-2024-007 | 3M Philippines Inc. | Safety Vest High-Visibility XL | 300 | 300 | 0 | 2024-01-27 | Safety Officer J. Cruz | ✅ Passed | Safety Officer J. Cruz | Good Condition | PPE Storage Room | Complete delivery
GR-2024-008 | PO-2024-008 | Petron Corporation | Diesel Fuel (liters) | 10000 | 10000 | 0 | 2024-01-28 | Fuel In-charge R. Santos | ✅ Passed | Admin Manager P. Lim | Delivered to Tank | Fuel Depot Site A | Delivery receipt on file
GR-2024-009 | PO-2024-009 | Holcim Philippines Inc. | Portland Cement Type I (40kg bag) | 3000 | 3000 | 0 | 2024-02-12 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site A - Bodega 1 | Complete
GR-2024-010 | PO-2024-010 | Lafarge Holcim Trading | Washed Sand (cubic meter) | 200 | 195 | -5 | 2024-02-14 | Warehse Keeper M. Santos | ⚠ Partial | QC Inspector B. Tan | Good Condition | Site A - Aggregate Yard | Slight shortage noted
GR-2024-011 | PO-2024-011 | Lafarge Holcim Trading | Crushed Gravel 3/4 inch (cubic meter) | 150 | 150 | 0 | 2024-02-14 | Warehse Keeper M. Santos | ✅ Passed | QC Inspector B. Tan | Good Condition | Site A - Aggregate Yard | Complete
GR-2024-012 | PO-2024-012 | SteelAsia Manufacturing | Deformed Steel Bar 16mm x 6m | 2000 | 2000 | 0 | 2024-02-26 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site A - Steel Yard | MTR received
GR-2024-013 | PO-2024-013 | HP Philippines Inc. | HP LaserJet Pro M404dn Printer | 10 | 10 | 0 | 2024-02-22 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | Serial nos. registered
GR-2024-014 | PO-2024-014 | National Book Store Inc. | Bond Paper A4 80gsm (ream) | 200 | 200 | 0 | 2024-02-21 | Admin Staff L. Bautista | ✅ Passed | Admin Officer S. Mendoza | Good Condition | Office Supply Room | Complete
GR-2024-015 | PO-2024-022 | Komatsu Philippines Inc. | Komatsu PC200-10 Excavator (unit) | 1 | 1 | 0 | 2024-04-15 | Equipment Mgr D. Ramos | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site B Equipment Yard | PDI completed, COC received
GR-2024-016 | PO-2024-024 | CEMEX Holdings PH | CEMEX Asenso Ready Mix Cement (40kg) | 2500 | 2500 | 0 | 2024-04-09 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site B - Bodega 1 | Complete
GR-2024-017 | PO-2024-031 | Dell Technologies PH | Dell OptiPlex 7010 Desktop PC | 15 | 15 | 0 | 2024-05-09 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | DOA check done
GR-2024-018 | PO-2024-039 | Lenovo Philippines | Lenovo ThinkPad E15 Gen5 Laptop | 8 | 8 | 0 | 2024-06-10 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | Registered with Lenovo
GR-2024-019 | PO-2024-047 | ABB Philippines Inc. | ABB Transformer 500kVA 13.8kV/400V | 1 | 1 | 0 | 2024-07-24 | Engr. M. Dela Cruz | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site B Substation | Factory test cert received
GR-2024-020 | PO-2024-052 | Schneider Electric PH | Schneider EasyPact MVS 800A ACB | 4 | 4 | 0 | 2024-08-16 | Engr. M. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Excellent | Electrical Store B | Complete w/ FAT docs
GR-2024-021 | PO-2024-054 | CEMEX Holdings PH | CEMEX Ready Mix Concrete 3000 PSI (m3) | 500 | 480 | -20 | 2024-08-15 | QC Engr. P. Santos | ⚠ Partial | QC Inspector A. Reyes | Good Condition | Site C - Pour Area | 20m3 short pour, rescheduled
GR-2024-022 | PO-2024-056 | Dell Technologies PH | Dell PowerEdge R750 Server | 2 | 2 | 0 | 2024-08-22 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Excellent | Data Center Room | Rack-mounted & tested
GR-2024-023 | PO-2024-060 | EEI Corporation | EEI Civil Works - Site C Foundation | 1 | 1 | 0 | 2024-10-05 | Project Engr. R. Torres | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site C | Progress cert no. 1 of 3
GR-2024-024 | PO-2024-066 | Holcim Philippines Inc. | Holcim Solido Mastercem OPC 40kg | 4000 | 4000 | 0 | 2024-10-11 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site C - Bodega 1 | Complete
GR-2024-025 | PO-2024-067 | SteelAsia Manufacturing | Deformed Steel Bar 25mm x 6m | 1000 | 1000 | 0 | 2024-10-21 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site C - Steel Yard | MTR & MTC received
GR-2024-026 | PO-2024-078 | Sta. Clara International | Sta. Clara MEP Installation - Site B | 1 | 1 | 0 | 2024-12-15 | Project Engr. A. Mendoza | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site B MEP | Progress cert no. 1
GR-2024-027 | PO-2024-081 | Holcim Philippines Inc. | Portland Cement Type I (40kg bag) | 5000 | 5000 | 0 | 2024-12-10 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site C - Bodega 1 | Year-end bulk delivery
GR-2024-028 | PO-2024-082 | HP Philippines Inc. | HP EliteBook 840 G11 Laptop | 10 | 10 | 0 | 2024-12-12 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Excellent | IT Storage Room | Registered with HP
GR-2025-001 | PO-2025-001 | Holcim Philippines Inc. | Holcim Solido OPC 40kg | 4500 | 4500 | 0 | 2025-01-13 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site C - Bodega 1 | Complete delivery
GR-2025-002 | PO-2025-002 | SteelAsia Manufacturing | Deformed Steel Bar 32mm x 6m | 800 | 800 | 0 | 2025-01-22 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector B. Tan | Good Condition | Site C - Steel Yard | MTR on file
GR-2025-003 | PO-2025-004 | Schneider Electric PH | Schneider Prisma Plus G Panel 1600A | 2 | 2 | 0 | 2025-01-29 | Engr. M. Dela Cruz | ✅ Passed | VP-Operations E. Villanueva | Excellent | Elec Store C | FAT cert received
GR-2025-004 | PO-2025-007 | CEMEX Holdings PH | CEMEX OPC Premium Blend 40kg | 3000 | 3000 | 0 | 2025-02-11 | Warehse Keeper M. Santos | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site C - Bodega 2 | Complete
GR-2025-005 | PO-2025-009 | ABB Philippines Inc. | ABB ACS880 Drive 110kW Industrial | 3 | 3 | 0 | 2025-02-24 | Engr. M. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Excellent | Elec Store C | All drives tested
GR-2025-006 | PO-2025-010 | Komatsu Philippines Inc. | Komatsu WA380-8 Wheel Loader | 1 | 1 | 0 | 2025-03-14 | Equipment Mgr D. Ramos | ✅ Passed | CEO R. Navarro | Excellent | Site D Equipment Yard | PDI & commissioning done
GR-2025-007 | PO-2025-013 | Dell Technologies PH | Dell Latitude 5550 Laptop | 20 | 20 | 0 | 2025-03-10 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | All tagged & enrolled
GR-2025-008 | PO-2025-016 | EEI Corporation | EEI Structural Works - Site D (Progress 1) | 1 | 1 | 0 | 2025-04-12 | Project Engr. R. Torres | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site D | Progress cert no. 1 — 35%
GR-2025-009 | PO-2025-019 | Holcim Philippines Inc. | Holcim HiEarly Cement 40kg | 5000 | 5000 | 0 | 2025-04-08 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Bodega 1 | Complete delivery
GR-2025-010 | PO-2025-020 | SteelAsia Manufacturing | Deformed Steel Bar 12mm x 6m (Seismic) | 6000 | 5800 | -200 | 2025-04-17 | Warehse Keeper R. Dela Cruz | ⚠ Partial | QC Inspector B. Tan | Good Condition | Site D - Steel Yard | 200pcs on backorder
GR-2025-011 | PO-2025-025 | Siemens Philippines | Siemens HV/LV Transformer 1000kVA | 1 | 1 | 0 | 2025-05-26 | Engr. M. Dela Cruz | ✅ Passed | CEO R. Navarro | Excellent | Site D Substation | FAT & SAT completed
GR-2025-012 | PO-2025-033 | HP Philippines Inc. | HP ProOne 440 G9 AIO PC | 25 | 25 | 0 | 2025-06-16 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | Complete delivery
GR-2025-013 | PO-2025-034 | Volvo Financial Services | Volvo EC380E Crawler Excavator | 1 | 1 | 0 | 2025-07-12 | Equipment Mgr D. Ramos | ✅ Passed | CEO R. Navarro | Excellent | Site D Equipment Yard | Commissioning & training done
GR-2025-014 | PO-2025-036 | Holcim Philippines Inc. | Holcim Solido OPC 40kg | 6000 | 6000 | 0 | 2025-07-08 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Bodega 1 | Bulk delivery, on schedule
GR-2025-015 | PO-2025-037 | SteelAsia Manufacturing | Deformed Steel Bar 16mm x 6m (BIS) | 4000 | 4000 | 0 | 2025-07-18 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector B. Tan | Good Condition | Site D - Steel Yard | Complete w/ MTR
GR-2025-016 | PO-2025-038 | Sta. Clara International | Sta. Clara HVAC Installation - Site D (P1) | 1 | 1 | 0 | 2025-08-07 | Project Engr. A. Mendoza | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site D | Progress cert no. 1 — 40%
GR-2025-017 | PO-2025-041 | Schneider Electric PH | Schneider Altivar 630 VFD 185kW | 4 | 4 | 0 | 2025-08-18 | Engr. M. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Excellent | Elec Store D | Factory tested units
GR-2025-018 | PO-2025-042 | CEMEX Holdings PH | CEMEX Ready Mix 4000 PSI (m3) | 800 | 800 | 0 | 2025-08-13 | QC Engr. P. Santos | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Pour Area | Cylinder tests scheduled
GR-2025-019 | PO-2025-044 | Dell Technologies PH | Dell UltraSharp U2724D Monitor 27in | 30 | 30 | 0 | 2025-08-19 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | Pixel-perfect check done
GR-2025-020 | PO-2025-053 | Holcim Philippines Inc. | Holcim Solido OPC 40kg | 7000 | 7000 | 0 | 2025-10-15 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Bodega 2 | On time delivery
GR-2025-021 | PO-2025-054 | SteelAsia Manufacturing | Deformed Steel Bar 20mm x 6m | 3000 | 3000 | 0 | 2025-10-24 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector B. Tan | Good Condition | Site D - Steel Yard | MTR batch 25-10 received
GR-2025-022 | PO-2025-060 | EEI Corporation | EEI Structural Steel Erection - Site D (P1) | 1 | 1 | 0 | 2025-12-08 | Project Engr. R. Torres | ✅ Passed | VP-Operations E. Villanueva | Excellent | Site D | Progress cert no. 1 — 45%
GR-2025-023 | PO-2025-065 | Schneider Electric PH | Schneider Galaxy VS UPS 80kVA | 2 | 2 | 0 | 2025-12-17 | Engr. M. Dela Cruz | ✅ Passed | IT Manager F. Ocampo | Excellent | Data Center Site D | Load bank tested
GR-2025-024 | PO-2025-066 | Holcim Philippines Inc. | Holcim Solido OPC 40kg | 8000 | 8000 | 0 | 2025-12-12 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Bodega 2 | Year-end surge delivery
GR-2026-001 | PO-2026-001 | Holcim Philippines Inc. | Holcim Solido OPC 40kg | 8000 | 8000 | 0 | 2026-01-12 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Good Condition | Site D - Bodega 3 | Complete delivery
GR-2026-002 | PO-2026-002 | SteelAsia Manufacturing | Deformed Steel Bar 25mm x 6m | 2500 | 2500 | 0 | 2026-01-21 | Warehse Keeper R. Dela Cruz | ✅ Passed | QC Inspector B. Tan | Good Condition | Site D - Steel Yard | MTR 2026-01 on file
GR-2026-003 | PO-2026-003 | Schneider Electric PH | Schneider PM8000 Power Quality Meter | 8 | 8 | 0 | 2026-01-24 | Engr. M. Dela Cruz | ✅ Passed | QC Inspector A. Reyes | Excellent | Elec Store D | Calibration cert received
GR-2026-004 | PO-2026-004 | Dell Technologies PH | Dell Vostro 3530 Business Laptop | 25 | 25 | 0 | 2026-01-20 | IT Staff K. Navarro | ✅ Passed | IT Manager F. Ocampo | Good Condition | IT Storage Room | DOA check — all passed
GR-2026-005 | PO-2026-005 | 3M Philippines Inc. | 3M PPE Kit (Full Set per person) | 150 | 150 | 0 | 2026-01-22 | Safety Officer J. Cruz | ✅ Passed | Safety Officer J. Cruz | Good Condition | PPE Storage Room | Lot numbers recorded
GR-2026-006 | PO-2026-006 | Petron Corporation | Diesel Fuel (Industrial liters) | 40000 | 40000 | 0 | 2026-01-30 | Fuel In-charge R. Santos | ✅ Passed | Admin Manager P. Lim | Delivered to Tank | Fuel Depot Site D | DR #2026-JAN-015

## AP Payment Tracker
💳 Pinnacle Construction & Development Corporation — ACCOUNTS PAYABLE & PAYMENT TRACKER
Invoice & Payment Records · Finance Division · 2024–2026
AP Record | PO Reference | Supplier Name | Invoice No. | Invoice Date | Invoice Amount (₱) | Due Date | Date Paid | Amount Paid (₱) | Outstanding (₱) | Days Outstanding | Payment Mode | Payment Status
AP-2024-001 | PO-2024-001 | Holcim Philippines Inc. | HPI-2024-00123 | 2024-01-15 | 625632 | 2024-02-14 | 2024-02-10 | 625632 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-002 | PO-2024-002 | SteelAsia Manufacturing | SA-INV-24-0089 | 2024-01-24 | 1075620 | 2024-02-23 | 2024-02-20 | 1075620 | 0 | 0 | Check | ✅ Paid
AP-2024-003 | PO-2024-003 | SteelAsia Manufacturing | SA-INV-24-0090 | 2024-01-24 | 926688 | 2024-02-23 | 2024-02-22 | 926688 | 0 | 0 | Check | ✅ Paid
AP-2024-004 | PO-2024-004 | Wilcon Depot Inc. | WILCON-2024-5678 | 2024-01-18 | 700000 | 2024-02-17 | 2024-02-12 | 700000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-005 | PO-2024-005 | Schneider Electric PH | SE-PH-2024-00456 | 2024-02-01 | 452200 | 2024-03-17 | 2024-03-14 | 452200 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-008 | PO-2024-008 | Petron Corporation | PCL-2024-JAN-089 | 2024-01-28 | 778400 | 2024-02-12 | 2024-02-10 | 778400 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-009 | PO-2024-009 | Holcim Philippines Inc. | HPI-2024-00234 | 2024-02-12 | 938448 | 2024-03-13 | 2024-03-10 | 938448 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-012 | PO-2024-012 | SteelAsia Manufacturing | SA-INV-24-0145 | 2024-02-26 | 1059072 | 2024-03-27 | 2024-03-25 | 1059072 | 0 | 0 | Check | ✅ Paid
AP-2024-013 | PO-2024-013 | HP Philippines Inc. | HP-PH-2024-0234 | 2024-02-22 | 196840 | 2024-03-23 | 2024-03-20 | 196840 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-017 | PO-2024-017 | Schneider Electric PH | SE-PH-2024-00567 | 2024-03-15 | 468160 | 2024-04-29 | 2024-04-25 | 468160 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-018 | PO-2024-018 | Siemens Philippines | SIE-PH-2024-0089 | 2024-03-25 | 461720 | 2024-05-09 | 2024-05-05 | 461720 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-022 | PO-2024-022 | Komatsu Philippines | KOM-2024-INV-001 | 2024-04-15 | 9520000 | 2024-05-30 | 2024-05-28 | 9520000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-024 | PO-2024-024 | CEMEX Holdings PH | CEMEX-2024-1234 | 2024-04-09 | 795760 | 2024-05-09 | 2024-05-06 | 795760 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-031 | PO-2024-031 | Dell Technologies PH | DELL-PH-2024-0567 | 2024-05-09 | 670320 | 2024-06-08 | 2024-06-05 | 670320 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-034 | PO-2024-034 | SteelAsia Manufacturing | SA-INV-24-0345 | 2024-05-24 | 1119552 | 2024-06-23 | 2024-06-20 | 1119552 | 0 | 0 | Check | ✅ Paid
AP-2024-039 | PO-2024-039 | Lenovo Philippines | LEN-PH-2024-0123 | 2024-06-10 | 578816 | 2024-07-10 | 2024-07-08 | 578816 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-047 | PO-2024-047 | ABB Philippines Inc. | ABB-PH-2024-0056 | 2024-07-24 | 2009840 | 2024-08-23 | 2024-08-20 | 2009840 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-052 | PO-2024-052 | Schneider Electric PH | SE-PH-2024-01234 | 2024-08-16 | 1238496 | 2024-09-30 | 2024-09-28 | 1238496 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-056 | PO-2024-056 | Dell Technologies PH | DELL-PH-2024-1234 | 2024-08-22 | 819280 | 2024-09-21 | 2024-09-18 | 819280 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-060 | PO-2024-060 | EEI Corporation | EEI-2024-PC-001 | 2024-10-05 | 14000000 | 2024-11-04 | 2024-11-02 | 14000000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-066 | PO-2024-066 | Holcim Philippines Inc. | HPI-2024-01345 | 2024-10-11 | 1295168 | 2024-11-10 | 2024-11-08 | 1295168 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-067 | PO-2024-067 | SteelAsia Manufacturing | SA-INV-24-0789 | 2024-10-21 | 1152480 | 2024-11-20 | 2024-11-18 | 1152480 | 0 | 0 | Check | ✅ Paid
AP-2024-069 | PO-2024-069 | ABB Philippines Inc. | ABB-PH-2024-0234 | 2024-10-28 | 1205904 | 2024-11-27 | 2024-11-25 | 1205904 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-072 | PO-2024-072 | Epson Philippines | EPS-PH-2024-0456 | 2024-10-27 | 191520 | 2024-11-26 | 2024-11-22 | 191520 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-075 | PO-2024-075 | Schneider Electric PH | SE-PH-2024-01567 | 2024-11-21 | 154812 | 2025-01-05 | 2025-01-03 | 154812 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-078 | PO-2024-078 | Sta. Clara International | SCI-2024-PC-001 | 2024-12-15 | 9520000 | 2025-01-14 | 2025-01-12 | 9520000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-081 | PO-2024-081 | Holcim Philippines Inc. | HPI-2024-02012 | 2024-12-10 | 1635424 | 2025-01-09 | 2025-01-07 | 1635424 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-082 | PO-2024-082 | HP Philippines Inc. | HP-PH-2024-2345 | 2024-12-12 | 1010800 | 2025-01-11 | 2025-01-09 | 1010800 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2024-085 | PO-2024-085 | Shell Philippines | SHELL-2024-DEC-078 | 2024-12-26 | 1828288 | 2025-01-10 | 2025-01-08 | 1828288 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-001 | PO-2025-001 | Holcim Philippines Inc. | HPI-2025-00123 | 2025-01-13 | 1491638.4 | 2025-02-12 | 2025-02-10 | 1491638.4 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-002 | PO-2025-002 | SteelAsia Manufacturing | SA-INV-25-0056 | 2025-01-22 | 1448832 | 2025-02-21 | 2025-02-18 | 1448832 | 0 | 0 | Check | ✅ Paid
AP-2025-004 | PO-2025-004 | Schneider Electric PH | SE-PH-2025-00123 | 2025-01-29 | 819280 | 2025-03-15 | 2025-03-12 | 819280 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-007 | PO-2025-007 | CEMEX Holdings PH | CEMEX-2025-0345 | 2025-02-11 | 981254.4 | 2025-03-13 | 2025-03-10 | 981254.4 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-009 | PO-2025-009 | ABB Philippines Inc. | ABB-PH-2025-0034 | 2025-02-24 | 1580712 | 2025-03-26 | 2025-03-24 | 1580712 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-010 | PO-2025-010 | Komatsu Philippines | KOM-2025-INV-001 | 2025-03-14 | 14000000 | 2025-04-28 | 2025-04-25 | 14000000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-013 | PO-2025-013 | Dell Technologies PH | DELL-PH-2025-0234 | 2025-03-10 | 1234240 | 2025-04-09 | 2025-04-07 | 1234240 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-016 | PO-2025-016 | EEI Corporation | EEI-2025-PC-001 | 2025-04-12 | 31920000 | 2025-05-12 |  | 15960000 | 15960000 | 346 | Bank Transfer | ⏳ Partially Paid
AP-2025-019 | PO-2025-019 | Holcim Philippines Inc. | HPI-2025-00567 | 2025-04-08 | 1728720 | 2025-05-08 | 2025-05-06 | 1728720 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-020 | PO-2025-020 | SteelAsia Manufacturing | SA-INV-25-0234 | 2025-04-17 | 1942752 | 2025-05-17 | 2025-05-15 | 1942752 | 0 | 0 | Check | ✅ Paid
AP-2025-025 | PO-2025-025 | Siemens Philippines | SIE-PH-2025-0045 | 2025-05-26 | 4096400 | 2025-07-10 | 2025-07-08 | 4096400 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-033 | PO-2025-033 | HP Philippines Inc. | HP-PH-2025-0789 | 2025-06-16 | 1463000 | 2025-07-16 | 2025-07-14 | 1463000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-034 | PO-2025-034 | Volvo Financial Svcs | VOLVO-2025-INV-001 | 2025-07-12 | 25200000 | 2025-09-10 |  | 12600000 | 12600000 | 225 | Bank Transfer | ⏳ Partially Paid
AP-2025-036 | PO-2025-036 | Holcim Philippines Inc. | HPI-2025-01234 | 2025-07-08 | 2028364.8 | 2025-08-07 | 2025-08-05 | 2028364.8 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-038 | PO-2025-038 | Sta. Clara International | SCI-2025-PC-001 | 2025-08-07 | 17696000 | 2025-09-06 |  | 8848000 | 8848000 | 229 | Bank Transfer | ⏳ Partially Paid
AP-2025-041 | PO-2025-041 | Schneider Electric PH | SE-PH-2025-01234 | 2025-08-18 | 3617600 | 2025-10-02 | 2025-09-30 | 3617600 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-042 | PO-2025-042 | CEMEX Holdings PH | CEMEX-2025-1234 | 2025-08-13 | 4928000 | 2025-09-12 | 2025-09-10 | 4928000 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-053 | PO-2025-053 | Holcim Philippines Inc. | HPI-2025-02345 | 2025-10-15 | 2397158.4 | 2025-11-14 | 2025-11-12 | 2397158.4 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-054 | PO-2025-054 | SteelAsia Manufacturing | SA-INV-25-0678 | 2025-10-24 | 2370816 | 2025-11-23 | 2025-11-20 | 2370816 | 0 | 0 | Check | ✅ Paid
AP-2025-060 | PO-2025-060 | EEI Corporation | EEI-2025-PC-002 | 2025-12-08 | 20720000 | 2026-01-07 |  | 0 | 20720000 | 106 | Bank Transfer | 🔴 Overdue
AP-2025-065 | PO-2025-065 | Schneider Electric PH | SE-PH-2025-02345 | 2025-12-17 | 3936800 | 2026-02-01 | 2026-01-28 | 3936800 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2025-066 | PO-2025-066 | Holcim Philippines Inc. | HPI-2025-03456 | 2025-12-12 | 2792294.4 | 2026-01-11 | 2026-01-09 | 2792294.4 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2026-001 | PO-2026-001 | Holcim Philippines Inc. | HPI-2026-00123 | 2026-01-12 | 2827417.6 | 2026-02-11 | 2026-02-09 | 2827417.6 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2026-002 | PO-2026-002 | SteelAsia Manufacturing | SA-INV-26-0012 | 2026-01-21 | 3018400 | 2026-02-20 |  | 0 | 3018400 | 62 | Check | 🔴 Overdue
AP-2026-003 | PO-2026-003 | Schneider Electric PH | SE-PH-2026-00045 | 2026-01-24 | 1574720 | 2026-03-10 |  | 0 | 1574720 | 44 | Bank Transfer | 📋 Pending
AP-2026-004 | PO-2026-004 | Dell Technologies PH | DELL-PH-2026-0045 | 2026-01-20 | 1010800 | 2026-02-19 | 2026-02-17 | 1010800 | 0 | 0 | Bank Transfer | ✅ Paid
AP-2026-005 | PO-2026-005 | 3M Philippines Inc. | 3M-PH-2026-0023 | 2026-01-22 | 814800 | 2026-02-21 |  | 0 | 814800 | 61 | Bank Transfer | 📋 Pending
AP-2026-006 | PO-2026-006 | Petron Corporation | PCL-2026-JAN-012 | 2026-01-30 | 3637760 | 2026-02-14 |  | 0 | 3637760 | 68 | Bank Transfer | 🔴 Overdue
AP-2026-007 | PO-2026-007 | Philippine Industrial Corp | PIC-2026-0034 | 2026-02-10 | 638400 | 2026-03-12 |  | 0 | 638400 | 42 | Bank Transfer | 📋 Pending
AP-2026-009 | PO-2026-009 | EEI Corporation | EEI-2026-PC-001 | 2026-03-01 | 39200000 | 2026-03-31 |  | 0 | 39200000 | 23 | Bank Transfer | 📋 Pending
AP-2026-013 | PO-2026-013 | Siemens Philippines | SIE-PH-2026-0012 | 2026-03-20 | 2713200 | 2026-05-04 |  | 0 | 2713200 | 0 | Bank Transfer | 📋 Pending
AP-2026-014 | PO-2026-014 | Sta. Clara International | SCI-2026-PC-001 | 2026-04-01 | 14000000 | 2026-05-01 |  | 0 | 14000000 | 0 | Bank Transfer | 📋 Pending
AP-2026-020 | PO-2026-020 | ABB Philippines Inc. | ABB-PH-2026-0012 | 2026-04-15 | 6192480 | 2026-05-15 |  | 0 | 6192480 | 0 | Bank Transfer | 📋 Pending

## Supplier Scorecard
⭐ Pinnacle Construction & Development Corporation — SUPPLIER PERFORMANCE SCORECARD
Annual Evaluation · Procurement Division · FY 2024–2025
Supplier ID | Supplier Name | Category | On-Time Delivery % | Quality Acceptance % | Invoice Accuracy % | Responsiveness (1-10) | Compliance Score (1-10) | Overall Score | Grade | Recommendation | Contract Status
SUP-001 | Holcim Philippines Inc. | Cement & Concrete | 98% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-002 | Republic Cement & Building Materials | Cement & Concrete | 91% | 95% | 98% | 8 | 8 | 28.6 | B | Review | Active
SUP-003 | CEMEX Holdings Philippines | Cement & Concrete | 96% | 97% | 99% | 9 | 9 | 32.1 | A | Renew | Active
SUP-004 | SteelAsia Manufacturing Corporation | Steel & Metal | 94% | 98% | 97% | 9 | 9 | 32.1 | A | Renew | Active
SUP-005 | Capital Steel Corporation | Steel & Metal | 89% | 94% | 96% | 8 | 7 | 26.9 | B | Review | Active
SUP-006 | Peerless Metal Industries Inc. | Steel & Metal | 82% | 88% | 90% | 6 | 7 | 23.3 | C | Probation | Watch List
SUP-007 | Wilcon Depot Inc. | Hardware & Tools | 95% | 96% | 99% | 9 | 8 | 30.4 | A | Renew | Active
SUP-008 | Ace Hardware Philippines Inc. | Hardware & Tools | 97% | 97% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-009 | Schneider Electric Philippines | Electrical & Mechanical | 99% | 100% | 100% | 10 | 10 | 35.6 | A+ | Renew & Expand | Active Premium
SUP-010 | Siemens Philippines Inc. | Electrical & Mechanical | 97% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-011 | ABB Philippines Inc. | Electrical & Mechanical | 98% | 100% | 100% | 10 | 10 | 35.6 | A+ | Renew & Expand | Active Premium
SUP-012 | Legrand Philippines Inc. | Electrical & Mechanical | 93% | 96% | 98% | 8 | 8 | 28.6 | A | Renew | Active
SUP-013 | 3M Philippines Inc. | Safety Equipment | 99% | 100% | 100% | 10 | 10 | 35.6 | A+ | Renew & Expand | Active Premium
SUP-014 | Honeywell Philippines Inc. | Safety Equipment | 90% | 97% | 98% | 8 | 8 | 28.6 | B | Review | Active
SUP-015 | Petron Corporation | Fuel & Lubricants | 97% | 98% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-016 | Shell Philippines Exploration | Fuel & Lubricants | 98% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-017 | Chevron Philippines Inc. | Fuel & Lubricants | 94% | 97% | 98% | 8 | 8 | 28.6 | A | Renew | Active
SUP-018 | HP Philippines Inc. | IT Equipment | 98% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-019 | Dell Technologies Philippines | IT Equipment | 99% | 100% | 100% | 10 | 10 | 35.6 | A+ | Renew & Expand | Active Premium
SUP-020 | Lenovo Philippines | IT Equipment | 92% | 96% | 98% | 8 | 8 | 28.6 | B | Review | Active
SUP-021 | Canon Marketing Philippines | IT Equipment | 97% | 98% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-022 | Epson Philippines Corporation | IT Equipment | 93% | 95% | 99% | 8 | 8 | 28.6 | B | Review | Active
SUP-023 | National Book Store Inc. | Office Supplies | 97% | 98% | 100% | 9 | 8 | 30.4 | A | Renew | Active
SUP-024 | Goldilocks Bookware & Office | Office Supplies | 83% | 90% | 92% | 6 | 7 | 23.3 | C | Probation | Watch List
SUP-025 | PLDT Inc. | Telecommunications | 90% | 92% | 100% | 8 | 8 | 28.6 | B | Review | Active
SUP-026 | Globe Telecom Inc. | Telecommunications | 91% | 93% | 100% | 8 | 8 | 28.6 | B | Review | Active
SUP-027 | Meralco | Utilities | 95% | 98% | 100% | 8 | 9 | 30.4 | A | Renew | Active
SUP-028 | Maynilad Water Services | Utilities | 80% | 88% | 95% | 6 | 7 | 23.3 | C | Probation | Watch List
SUP-029 | Lafarge Republic Inc. | Cement & Concrete | 88% | 93% | 96% | 7 | 7 | 25.1 | B | Review | Watch List
SUP-030 | Pacific Paint (Boysen) Philippines | Construction Materials | 94% | 96% | 99% | 8 | 8 | 28.6 | A | Renew | Active
SUP-031 | Davies Paints Philippines | Construction Materials | 93% | 95% | 99% | 8 | 8 | 28.6 | B | Review | Active
SUP-032 | Neltex Development Co. | Construction Materials | 91% | 94% | 97% | 8 | 7 | 26.9 | B | Review | Active
SUP-033 | Vyniles Corporation Philippines | Construction Materials | 74% | 82% | 85% | 5 | 6 | 19.8 | C | Probation | Under Review
SUP-034 | Dowell Schlumberger Philippines | Engineering Services | 97% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-035 | EEI Corporation | Engineering Services | 96% | 98% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-036 | Sta. Clara International Corporation | Engineering Services | 91% | 95% | 99% | 8 | 8 | 28.6 | B | Review | Active
SUP-037 | Komatsu Philippines Inc. | Heavy Equipment | 98% | 100% | 100% | 10 | 10 | 35.6 | A+ | Renew & Expand | Active Premium
SUP-038 | Volvo Financial Services Philippines | Heavy Equipment | 96% | 99% | 100% | 9 | 9 | 32.1 | A+ | Renew & Expand | Active Premium
SUP-039 | Lafarge Holcim Trading Philippines | Aggregates & Sand | 93% | 95% | 98% | 8 | 8 | 28.6 | B | Review | Active
SUP-040 | Philippine Industrial Corporation | Chemicals & Sealants | 82% | 88% | 90% | 7 | 7 | 25.1 | B | Review | Watch List

## Procurement Dashboard
📊 Pinnacle Construction & Development Corporation — PROCUREMENT ANALYTICS DASHBOARD | [9 empty] | Month | PO Spend (₱M) | Category | Value (₱M)
Key Metrics & Visual Analytics · Procurement Division · FY 2024–2026 · Generated: April 23, 2026 | [9 empty] | Jan-24 | 3.35 | Cement & Concrete | 124.85
[10 empty] | Feb-24 | 5.24 | Steel & Metal | 89.25
TOTAL POs ISSUED |  |  |  | TOTAL PO VALUE |  |  |  | ACTIVE SUPPLIERS | ON-TIME DELIVERY | Mar-24 | 9.85 | Engineering Services | 130.8
105 |  |  |  | ₱485.2M |  |  |  | 40 | 94.2% | Apr-24 | 9.25 | Electrical & Mechanical | 68.95
FY 2024–2026 |  |  |  | All POs 2024–2026 |  |  |  | Accredited Vendors | 2024–2025 Average | May-24 | 5.85 | Heavy Equipment | 71
[10 empty] | Jun-24 | 4.25 | Fuel & Lubricants | 29.85
📦 SPEND BY CATEGORY | [9 empty] | Jul-24 | 10.85 | IT Equipment | 15.25
Category | No. of POs | Total Value (₱) | % of Total | Avg PO Size (₱) | Top Supplier | On-Time % | Quality % |  |  | Aug-24 | 9.48 | Safety Equipment | 5.45
Cement & Concrete | 18 | 124850000 | 22.71% | 6936111.1111 | Holcim Philippines Inc. | 98% | 99% |  |  | Sep-24 | 13.28 | Construction Materials | 4.98
Steel & Metal | 16 | 89250000 | 16.24% | 5578125 | SteelAsia Manufacturing Corp. | 93% | 97% |  |  | Oct-24 | 12.58 | Aggregates & Sand | 4.85
Engineering Services | 6 | 130800000 | 23.79% | 21800000 | EEI Corporation | 95% | 98% |  |  | Nov-24 | 9.85 | Office Supplies | 1.25
Electrical & Mechanical | 18 | 68950000 | 12.54% | 3830555.5556 | Schneider Electric Philippines | 97% | 99% |  |  | Dec-24 | 8.95 | Chemicals & Sealants | 2.85
Heavy Equipment | 4 | 71000000 | 12.92% | 17750000 | Komatsu Philippines Inc. | 98% | 100% |  |  | Jan-25 | 3.25 | Telecommunications | 0.21
Fuel & Lubricants | 20 | 29850000 | 5.43% | 1492500 | Petron Corporation / Shell | 97% | 98% |  |  | Feb-25 | 15.25 | Utilities | 0.185
IT Equipment | 12 | 15250000 | 2.774% | 1270833.3333 | Dell Technologies Philippines | 98% | 99% |  |  | Mar-25 | 34.8
Safety Equipment | 10 | 5450000 | 0.9914% | 545000 | 3M Philippines Inc. | 99% | 100% |  |  | Apr-25 | 9.85
Construction Materials | 8 | 4980000 | 0.9059% | 622500 | Boysen / Neltex / Davies | 92% | 95% |  |  | May-25 | 28.5
Aggregates & Sand | 8 | 4850000 | 0.8823% | 606250 | Lafarge Holcim Trading PH | 93% | 95% |  |  | Jun-25 | 24.5
Office Supplies | 6 | 1250000 | 0.2274% | 208333.3333 | National Book Store Inc. | 96% | 98% |  |  | Jul-25 | 18.98
Chemicals & Sealants | 4 | 2850000 | 0.5184% | 712500 | Philippine Industrial Corp. | 82% | 88% |  |  | Aug-25 | 10.25
Telecommunications | 2 | 210000 | 0.0382% | 105000 | PLDT Inc. / Globe Telecom | 90% | 92% |  |  | Sep-25 | 5.85
Utilities | 1 | 185000 | 0.03365% | 185000 | Meralco | 95% | 98% |  |  | Oct-25 | 9.85
[10 empty] | Nov-25 | 21.25
[10 empty] | Dec-25 | 6.85
[10 empty] | Jan-26 | 8.5
[10 empty] | Feb-26 | 36.85
[10 empty] | Mar-26 | 48.5
[10 empty] | Apr-26 | 8.85